ProverbGap: Measuring the Cultural Reasoning Gap in Large Language Models

Project Status Document for Steven Kolawole   April 24, 2026

Prepared by Aspita , Jesuyanmife , Iremide

SUMMARY

1. ProverbGap is a 6-language, two-task MCQ benchmark measuring the

Cultural Reasoning Gap   the difference between literal and cultural

proverb understanding in LLMs.

2. We have 36 CSV files with ~32,000 MCQ items already generated across

2 tasks × 3 strategies × 6 languages. Quality scores range 79-99/100.

3. The benchmark introduces three novel contributions:

(a) Two-task literal/cultural split (no prior work has this)

(b) Automated LLM-generated distractors at scale with audit protocol

(c) First cultural reasoning evaluation for AfriqueLLM models

4. Key finding preview: Task B (cultural) blind audit accuracy is 90%+

for European languages but 66.9% for Yoruba   the Cultural Reasoning

Gap is largest for low-resource African languages.

5. Remaining work: Phase 2 evaluation (2 weeks), length patch (1 day),

AfriqueLLM evaluation (1 week), paper writing (2 weeks).

6. Target venues: EMNLP 2026 (ARR May 2026, submit May 25, conference

Oct 24-29 Budapest) or NeurIPS 2026 Evaluations & Datasets track

(submit May 4-6, conference Dec 6-12 Sydney). Both accept benchmark

papers combining MCQ + fill-in-blank + generation.

1. WHAT IS PROVERBGAP?

ProverbGap is a multilingual benchmark that measures how well LLMs understand

proverbs   not just their literal translations, but their deeper cultural

meanings. We test this by generating multiple-choice questions (MCQs) where

models must distinguish correct proverb meanings from plausible distractors.

Core idea: For any proverb, there are two levels of understanding:

Task A (Literal): What does this proverb say word-for-word in English?

Task B (Cultural): What life lesson or cultural wisdom does it convey?

The gap between model performance on Task A vs Task B = the "Cultural

Reasoning Gap"   our primary finding. A model that scores 90% on literal

but only 55% on cultural meaning has a 35-percentage-point gap, revealing

it can translate but cannot reason about culture.

Why this matters: Existing proverb benchmarks (ProverbEval, Azime et al.

NAACL 2025) used only 500 Ethiopian proverbs with human-annotated MCQs.

We scale to 6 languages, 5,444 proverbs, automated generation, and

introduce the two-task literal/cultural split   a design no prior work has.

1.1 RESEARCH QUESTIONS

RQ1: Do LLMs exhibit a measurable Cultural Reasoning Gap   a systematic

performance difference between literal proverb translation (Task A)

and cultural meaning interpretation (Task B)?

RQ2: How does this gap vary across languages of different resource levels

(low-resource Yoruba, mid-resource Arabic, high-resource English/

European languages)?

RQ3: Does continued pre-training on African language data (AfriqueLLM)

narrow the Cultural Reasoning Gap for Yoruba proverbs compared to

base models of equivalent size?

RQ4: How do prompting strategies (zero-shot, CoT in English, CoT in the

proverb's source language) affect cultural reasoning accuracy, and

does cross-lingual CoT provide gains for low-resource languages?

RQ5: Can LLM-generated MCQ distractors achieve sufficient quality at

scale, as validated by blind shortcut audits, to replace human

annotation for cultural reasoning benchmarks?

1.2 HYPOTHESES

H1: Models will score significantly higher on Task A (literal) than

Task B (cultural), with the largest gap for low-resource languages.

H2: The Cultural Reasoning Gap will be inversely correlated with language

resource level: largest for Yoruba, moderate for Arabic, smallest for

English and European languages.

H3: AfriqueLLM models will outperform their base counterparts on Yoruba

cultural proverb understanding (Task B), narrowing the gap.

H4: Cross-lingual Chain-of-Thought prompting will improve performance

for non-English languages, particularly Yoruba, by keeping the model

in the source-language embedding space during reasoning.

1.3 CONTRIBUTIONS

C1: The Cultural Reasoning Gap metric   a principled two-task evaluation

design that separates literal from cultural understanding of proverbs.

C2: ProverbGap dataset   ~32,000 MCQ items across 6 languages and 3

resource tiers, with automated LLM-generated distractors validated

by blind shortcut audits.

C3: First cultural reasoning evaluation of AfriqueLLM models

measuring whether Africa-focused continued pre-training narrows the

gap for Yoruba proverbs.

C4: A three-format evaluation pyramid (MCQ + Fill-in-Blank + Free-form

Generation) that assesses receptive, productive, and open-ended

cultural knowledge.

C5: Reusable shortcut audit protocol and length-constrained regeneration

pipeline for MCQ benchmark quality assurance.

2. RELATION TO PROVERBEVAL

We originally named this project "ProverbEval." During development, we

discovered Azime et al. had already published a paper titled "ProverbEval"

at NAACL 2025 Findings for Ethiopian languages. We renamed to "ProverbGap"

to avoid confusion and to better reflect our contribution   measuring the

GAP in cultural reasoning, not just evaluating comprehension.

Key differences from Azime et al. (NAACL 2025):

| Dimension | ProverbEval (Azime) | ProverbGap (Ours) |
| --- | --- | --- |
| Languages | 4 (Ethiopian) | 6 (3 resource tiers) |
| Proverbs | ~500 | 5,444 |
| Distractor source | Human volunteers | LLM-generated + audited |
| Tasks | MCQ only | MCQ literal + cultural |
| Cultural reasoning gap | Not measured | Primary contribution |
| Evaluation format | MCQ, fill-in-blank | MCQ (two-task), CoT, FIB |
| Models tested | Not specified | 3+ models, 3 sizes |
| Open dataset | Limited | Full release planned |

3. CORPUS: WHERE THE DATA COMES FROM

| Language | Proverbs | Resource Tier | Source |
| --- | --- | --- | --- |
| Yoruba | 3,500+ | Low-resource | OCR-extracted from a published book of Yoruba proverbs. Manually cleaned. Full corpus: 3,500+ proverbs (cleaned). Limited to 2,000 for generation runs. |
| Arabic | 803 | Mid-resource | HuggingFace (publicly available CSV) |
| English | 2,278 | High-resource | HuggingFace (English_Corpus_clean.csv) |
| French | 160 | High-resource | Web-scraped from proverb websites |
| German | 141 | High-resource | HuggingFace (publicly available CSV) |
| Spanish | 62 | High-resource | HuggingFace (publicly available CSV) |
| TOTAL | 5,444 |  | Using 2,000 Yoruba cap |

IMPORTANT   The Full Yoruba Corpus as a Standalone Contribution:

The complete, cleaned Yoruba proverb corpus contains 3,500+ proverbs

the largest digitised collection of Yoruba proverbs with parallel English

translations and cultural context annotations that we are aware of. This

corpus is itself a significant data contribution to low-resource NLP,

independent of the MCQ benchmark. We plan to release it as a standalone

dataset submission alongside the ProverbGap benchmark paper.

Each source proverb has three columns:

1. Proverb   the original text in the source language

2. Translation   literal English word-for-word meaning

3. Cultural_Context   the deeper cultural lesson

For English proverbs, Translation == Cultural_Context (English is

"culturally transparent"   the literal and cultural meanings align).

This is itself a finding we report.

Licensing:

Arabic, English, French, German, Spanish: CC BY 4.0

Yoruba: CC BY-NC 4.0 (derived from copyrighted book; MCQ items are

our contribution, released with access-request mechanism)

Busayo's feedback on languages (April 3 meeting): Consider swapping one

European language for a mid-tier non-European or additional low-resource

language (e.g., Haitian, Samoan, Indian language). We note this as a

valid suggestion for future work. For this submission, we retain all 6

because: (a) the data is already cleaned and generated, (b) French/German/

Spanish serve as a high-resource control group, (c) the paper's core

finding is the Yoruba/Arabic vs English/European gap, not language count.

4. HOW MCQ GENERATION WORKS

4.1 The Pipeline

Step 1: Feed the LLM a correct meaning (literal OR cultural)

Step 2: LLM generates 3 plausible-but-wrong alternatives (distractors)

Step 3: Quality check   parse rate, completeness, distinctness

Step 4: Assemble into 4-choice MCQ with randomized answer position

Step 5: Shortcut audit   can a blind evaluator guess the answer?

Step 6: Length audit   are correct answers systematically longer?

Critical clarification (from Busayo's question in the meeting): We do NOT

ask the LLM to understand or interpret the proverb. We feed it a plain

English sentence (the meaning) and ask it to generate similar-sounding

but incorrect alternatives. The LLM never sees the original proverb

during generation. This is distractor generation, not comprehension testing.

4.2 Three Prompting Strategies

| Strategy | System Prompt Approach | Generator Model |
| --- | --- | --- |
| Zero-Shot (ZS) | "Generate 3 wrong meanings. JSON only." | Cerebras Qwen3-235B |
| CoT-English | "Reason in English, then generate." | Groq LLaMA-3.3-70B |
| CoT-CrossLing | "Reason in the proverb's language." | Groq LLaMA-3.1-8B |

4.3 Why These Models?

We ran a formal pilot study testing 8 models across 3 providers on 60

proverbs per combination (documented in proverbgap_prompt_model_cmp.ipynb).

| Model | Provider | Params | Year | ZS Score | CoT-EN |
| --- | --- | --- | --- | --- | --- |
| Qwen3-235B | Cerebras | 235B | 2025 | 98.7 |  |
| Kimi-K2* | Groq | 1T | 2025 | 97.9 | 97.8 |
| LLaMA 3.3-70B | Groq | 70B | 2024 | 96.1 | 97.5 |
| LLaMA 3.1-8B | Groq | 8B | 2024 | 96.4 | 95.8 |
| LLaMA 4 Scout | Groq | 17B | 2025 | 94.0 |  |
| Qwen3-32B | Groq | 32B | 2025 | 87.2 |  |
| GPT-OSS-120B (Nemotron) | NVIDIA | 120B | 2025 |  |  |
| GPT-OSS-20B | Groq | 20B | 2025 | 16.3 |  |

Kimi-K2 was our initial ZS choice but was discovered to have a fatal

bug: it uses <think> tags that consume all 2,000 max_tokens during

internal reasoning, producing 0% parse rate in production. Replaced

with Cerebras Qwen3-235B (pilot winner).

Model selection rationale:

ZS: Cerebras Qwen3-235B   highest pilot score (98.7), free tier

(1M tokens/day, 30 RPM), 2025 model

CoT-EN: Groq LLaMA-3.3-70B   strongest CoT performer (97.5), high

throughput (8,000 RPD across 8 API keys)

CoT-XL: Groq LLaMA-3.1-8B   best cross-lingual reasoning (96.6),

fast inference

Evaluator: Groq LLaMA-3.1-8B   14,400 RPD capacity for blind audit

4.4 Discovery of NVIDIA as a Provider

During development, we hit Groq's daily rate limits repeatedly (1,000 RPD

per key, ~8,000/day with 8 keys). We discovered NVIDIA's build.nvidia.com

API provides free-tier access to nvidia/nemotron-3-super-120b-a12b (120B

params). We integrated NVIDIA as:

Fallback for Groq-exhausted strategies (when all 8 keys hit daily cap)

Second evaluator in the shortcut audit committee (two-model blind vote)

ZS overflow when Cerebras rate-limits during high-traffic periods

The NVIDIA integration proved critical in our current production run:

all 8 Groq keys were exhausted within 26 seconds of starting, and NVIDIA

took over CoT-English generation for 1,927 remaining Yoruba rows.

5. QUALITY ASSURANCE: SHORTCUT AUDIT

Problem: If distractors are obviously wrong ("Do bad things" vs "Act

wisely at the right time"), a model can score high without understanding

the proverb at all   just by picking the most "positive-sounding" option.

This is the "shortcut" bias (Balepur et al. 2026, BenchMarker).

Our audit protocol (Balepur et al. 2026, BenchMarker):

1. A blind evaluator LLM (LLaMA-3.1-8B) sees only the proverb + 4 choices

2. It does NOT see which answer is correct

3. If it can still guess correctly >45% of the time (vs 25% random),

the distractors have surface shortcuts

Current audit results (from completed mcq_results):

| Task | Language | Blind Acc% | vs 25% | Status |
| --- | --- | --- | --- | --- |
| A | Yoruba | 72.0% | +47.0pp | FLAGGED (length) |
| A | German | 63.1% | +38.1pp | FLAGGED (length) |
| A | Spanish | 54.8% | +29.8pp | FLAGGED (length) |
| A | French | 49.4% | +24.4pp | FLAGGED (length) |
| A | English | 34.4% | +9.4pp | ACCEPTABLE |
| A | Arabic | 28.4% | +3.4pp | ACCEPTABLE |
| B | Spanish | 95.2% | +70.2pp | EXPECTED (see §5.1) |
| B | German | 92.2% | +67.2pp | EXPECTED |
| B | English | 90.0% | +65.0pp | EXPECTED |
| B | French | 82.5% | +57.5pp | EXPECTED |
| B | Arabic | 80.8% | +55.8pp | EXPECTED |
| B | Yoruba | 66.9% | +41.9pp | CULTURAL GAP SIGNAL |

5.1 Why Task B Audit Numbers Are High (And That's OK)

Task B asking about cultural meaning is inherently easier for high-resource

languages (English, German, Spanish) because these languages are well-

represented in LLM training data. The evaluator "knows" the cultural meaning

that IS the cultural transparency we're measuring. Yoruba's lower Task B

score (66.9% vs 90%+ for European languages) IS the Cultural Reasoning

Gap: the model struggles more with Yoruba cultural meanings because Yoruba

is underrepresented in training data.

5.2 Length Shortcut Diagnosis and Fix

Root cause for Task A flags: Correct answers averaged 15.6 words while

distractors averaged 12.2 words. 416 items (17.6%) had correct answers

>1.6x longer than mean distractor length   a surface cue.

Fix: Length-constrained regeneration using Cerebras Qwen3-235B with prompt:

"Each distractor must be within ±3 words of the correct answer length."

Separate notebook created (ProverbGap_LengthPatch_Kaggle.ipynb) targeting

354 Yoruba + 28 French + 24 German + 10 Spanish items.

Status: Patch notebook ready, awaiting execution after current run completes.

6. AFRIQUELLM   PLANNED EVALUATION MODELS

AfriqueLLM (Yu et al., arXiv:2601.06395, January 2026) is a suite of open

LLMs adapted to 20 African languages through continued pre-training on 26B

tokens, released by McGill NLP (David Ifeoluwa Adelani et al.).

Available models (from HuggingFace McGill-NLP collection):

AfriqueLlama-8B (based on LLaMA 3.1)

AfriqueGemma-4B, AfriqueGemma-12B (based on Gemma 3)

AfriqueQwen-4B, AfriqueQwen-8B, AfriqueQwen-14B (based on Qwen 3)

AfriqueQwen3.5-4B, AfriqueQwen3.5-4B-ExtendedCM

Why this matters for ProverbGap: AfriqueLLM models are specifically adapted

for African languages including Yoruba. Evaluating ProverbGap MCQs against

AfriqueLLM models (in addition to base models) lets us measure whether

Africa-focused continued pre-training narrows the Cultural Reasoning Gap.

Planned comparison:

Base LLaMA-3.1-8B vs AfriqueLlama-8B on Yoruba Task A/B

Base Gemma-12B vs AfriqueGemma-12B on Yoruba Task A/B

Base Qwen-14B vs AfriqueQwen-14B on Yoruba Task A/B

→ Does Africa-adapted CPT improve cultural proverb understanding?

This is a strong contribution: no existing benchmark has evaluated

AfriqueLLM on cultural reasoning tasks. ProverbGap would be the first.

Access: All models are open-weight on HuggingFace. Can run via Ollama

locally or on Kaggle GPU (T4/P100 for 4-8B, A100 for 12-14B).

7. CURRENT GENERATION STATUS (AS OF APRIL 24, 2026)

7.1 Completed MCQ Generation (from mcq_results dataset):

| Task | Strategy | Language | Model | Items | Parse% | Quality |
| --- | --- | --- | --- | --- | --- | --- |
| A | ZS | Yoruba | Qwen3-235B | 2,000 | 99.6% | 95.8 |
| A | ZS | Arabic | Qwen3-235B | 803 | 100.0% | 93.4 |
| A | ZS | English | Qwen3-235B | 2,278 | 99.9% | 96.6 |
| A | ZS | French | Qwen3-235B | 160 | 100.0% | 95.7 |
| A | ZS | Spanish | Qwen3-235B | 62 | 100.0% | 96.6 |
| A | ZS | German | Qwen3-235B | 141 | 100.0% | 94.8 |
| A | CoT-EN | Yoruba | LLaMA-3.3-70B | 2,000 | 99.2% | 95.1 |
| A | CoT-EN | Arabic | LLaMA-3.3-70B | 803 | 99.1% | 94.0 |
| A | CoT-EN | English | LLaMA-3.3-70B | 2,161 | 100.0% | 95.3 |
| A | CoT-EN | French | LLaMA-3.3-70B | 160 | 93.8% | 89.7 |
| A | CoT-EN | Spanish | LLaMA-3.3-70B | 62 | 93.5% | 90.0 |
| A | CoT-EN | German | LLaMA-3.3-70B | 141 | 98.6% | 93.8 |
| A | CoT-XL | Yoruba | LLaMA-3.1-8B | 2,000 | 89.4% | 82.6 |
| A | CoT-XL | Arabic | LLaMA-3.1-8B | 803 | 91.2% | 82.4 |
| A | CoT-XL | English | LLaMA-3.1-8B | 2,278 | 90.6% | 84.7 |
| A | CoT-XL | French | LLaMA-3.1-8B | 160 | 89.4% | 82.9 |
| A | CoT-XL | Spanish | LLaMA-3.1-8B | 62 | 87.1% | 79.5 |
| A | CoT-XL | German | LLaMA-3.1-8B | 141 | 92.2% | 83.3 |
| B | ZS | Yoruba | Qwen3-235B | 2,000 | 99.0% | 97.8 |
| B | ZS | Arabic | Qwen3-235B | 803 | 100.0% | 98.4 |
| B | ZS | English | Qwen3-235B | 2,278 | 99.9% | 96.6 |
| B | ZS | French | Qwen3-235B | 160 | 98.8% | 97.4 |
| B | ZS | Spanish | Qwen3-235B | 62 | 100.0% | 99.1 |
| B | ZS | German | Qwen3-235B | 141 | 100.0% | 98.6 |
| B | CoT-EN | Yoruba | LLaMA-3.3-70B | 2,000 | 99.1% | 96.5 |
| B | CoT-EN | Arabic | LLaMA-3.3-70B | 803 | 100.0% | 96.8 |
| B | CoT-EN | English | LLaMA-3.3-70B | 2,278 | 100.0% | 96.3 |
| B | CoT-EN | French | LLaMA-3.3-70B | 160 | 100.0% | 97.4 |
| B | CoT-EN | Spanish | LLaMA-3.3-70B | 62 | 100.0% | 97.1 |
| B | CoT-EN | German | LLaMA-3.3-70B | 141 | 100.0% | 96.6 |
| B | CoT-XL | Yoruba | LLaMA-3.1-8B | 2,000 | 99.3% | 95.6 |
| B | CoT-XL | Arabic | LLaMA-3.1-8B | 803 | 98.8% | 95.0 |
| B | CoT-XL | English | LLaMA-3.1-8B | 2,002 | 99.1% | 94.8 |
| B | CoT-XL | French | LLaMA-3.1-8B | 160 | 98.8% | 95.2 |
| B | CoT-XL | Spanish | LLaMA-3.1-8B | 62 | 100.0% | 96.6 |
| B | CoT-XL | German | LLaMA-3.1-8B | 141 | 97.9% | 94.2 |

Total: 36 CSV files, ~32,000 MCQ items across all tasks/strategies/languages.

7.1.1 MCQ CSV Column Descriptions

Each generated MCQ CSV file contains the following 22 columns:

| Column | Description |
| --- | --- |
| task | "a" (literal meaning) or "b" (cultural meaning) |
| strategy | "zs" (zero-shot), "cot_en" (CoT English), |
|  | or "cot_xl" (CoT cross-lingual) |
| language | Source language of the proverb |
| sample_id | Unique proverb identifier (e.g., YOR0001) |
| source_proverb | Original proverb in the source language |
| proverb_en | English translation of the proverb |
| correct_meaning | The correct answer (literal or cultural meaning) |
| cultural_context_available | Whether cultural context was provided (True/False) |
| Choice_A – Choice_D | The four MCQ options in randomised order |
| Answer | Correct answer letter (A, B, C, or D) |
| distractor_1 – distractor_3 | The three LLM-generated wrong alternatives |
| raw_response | Raw JSON from the LLM API call |
| parse | Parse success score (0.0 or 1.0) |
| complete | Completeness score (0.0 or 1.0) all 3 |
|  | distractors present and non-empty |
| len_r | Length ratio avg distractor length / correct |
|  | answer length (closer to 1.0 = better) |
| distinct | Distinctness score semantic diversity among |
|  | the 3 distractors (higher = less repetition) |
| quality | Composite quality score (0–100) combining |
|  | parse, complete, len_r, and distinct |

Each audit CSV file contains 6 columns:

| Column | Description |
| --- | --- |
| task | "a" or "b" |
| sample_id | Matches the generation CSV sample_id |
| language | Source language |
| correct_pos | Position of correct answer (A/B/C/D) |
| eval_answer | The blind evaluator's chosen answer letter |
| eval_correct | 1 if eval_answer == correct_pos, else 0 |

7.2 Current MCQ Regeneration Status (as of April 24, 2026)

We are regenerating all 36 CSV files with an optimized concurrent

pipeline to produce cleaner, audit-passing MCQs. This is NOT the first

generation   it is a quality-improvement regeneration using lessons

learned from the shortcut audit.

Pipeline architecture (running on Kaggle, 12h GPU session):

Cerebras ZS and Groq CoT run IN PARALLEL (different API providers)

8 Groq API keys dispatched in parallel workers per strategy

Checkpoint resume system: auto-detects prior CSVs and continues

from the last completed row (critical for multi-day runs)

NVIDIA fallback: when all Groq keys are exhausted, generation

continues via nvidia/nemotron-3-super-120b-a12b (slower, ~2.5 rows/min)

Live status snapshot (taken at ~6,000 seconds into current run):

Cerebras ZS Yoruba: batch 160/400 completed, parse=94%, quality=90

Groq CoT-EN Yoruba: all 8 keys exhausted in 26 seconds (daily caps

from earlier runs today). NVIDIA fallback active at row 240/1,927.

Groq CoT-XL: queued behind CoT-EN, not yet started this session.

Other languages (Arabic, English, French, German, Spanish): pending

after Yoruba completes.

Projected plan:

Current run will time out at Kaggle 12h limit.

Resume tomorrow (April 25) with fresh Groq daily quotas (8,000 RPD).

Estimated 2-3 more Kaggle sessions to complete all 36 CSVs.

Checkpoint resume ensures zero wasted work between sessions.

8. SETBACKS AND HOW WE RESOLVED THEM

Setback 1: Name Collision

Problem: "ProverbEval" already published at NAACL 2025

Impact: Had to rename, reframe, rewrite all documentation

Fix: Renamed to "ProverbGap"   stronger framing around the gap metric

Setback 2: Kimi-K2 Think Tag Bug

Problem: Kimi-K2 on Groq uses <think> tags that consume all 2,000

max_tokens during internal reasoning, producing 0% parse rate

Impact: Entire ZS strategy produced empty results in production

Discovery: Diagnosed by inspecting raw API responses   model was

"thinking" but never outputting actual distractors

Fix: Switched to Cerebras Qwen3-235B (pilot winner, 98.7% quality)

Setback 3: Groq Daily Rate Limits

Problem: 1,000 requests/day per key; 8 keys = 8,000 RPD total

Impact: Cannot complete 5,444 × 6 strategies in a single run

Fix: Multi-day generation with checkpoint resume system. Added NVIDIA

as fallback provider and Cerebras batching (5 proverbs/call).

Setback 4: Shortcut Distractors

Problem: First-generation distractors were obviously wrong   models

scored high without reading the proverb (shortcut bias)

Impact: Benchmark would be useless if shortcuts exist

Fix: Implemented Balepur et al. 2026 (BenchMarker) blind audit protocol. Identified

and flagged items. Developed length-constrained regeneration.

Setback 5: Length Disparity

Problem: Correct answers systematically 27% longer than distractors

Impact: 416 items (17.6%) flagged in 4 languages

Fix: Length-constrained prompt requiring ±3 word tolerance. Separate

patch notebook with Cerebras Qwen3-235B.

Setback 6: LLaMA 4 Maverick Deprecation

Problem: LLaMA 4 Maverick was our original generator   deprecated

from Groq on March 9, 2026

Fix: Replaced with LLaMA 3.3-70B (widely cited, strong performer)

Setback 7: VS Code Buffer Not Saving to Disk

Problem: Code edits made in VS Code notebook were not saved to the

.ipynb file on disk   Kaggle received the old code

Impact: Multiple wasted Kaggle runs (hours lost)

Fix: Created Python patch scripts (apply_all_fixes.py,

apply_concurrency_fixes.py) that directly manipulate the

notebook JSON on disk, bypassing the editor buffer issue.

Setback 8: Small Corpus Sizes for Some Languages

Problem: French (160), German (141), Spanish (62) are small

Impact: Reviewers may question statistical power

Mitigation: These serve as a high-resource control group. The core

finding is Yoruba (2,000) vs English (2,278). We report

effect sizes and confidence intervals.

9. WHAT WE PLAN TO DELIVER

9.1 Paper Deliverables (for EMNLP 2026 / NeurIPS 2026 submission)

Table 1: MCQ Accuracy   3 models × 6 languages × 2 tasks × 3 strategies

Table 2: Scaling Trend   8B vs 70B vs 235B accuracy curves

Table 3: Reasoning Gain   standard vs CoT (English vs cross-lingual)

Table 4: Context Gain   Task B no_context vs with_context

Table 5: Cultural Reasoning Gap   Task A accuracy minus Task B accuracy

per language (the core contribution)

Table 6: AfriqueLLM comparison   base vs Africa-adapted on Yoruba

Table 7: Shortcut audit results   blind evaluator accuracy per condition

9.2 Evaluation Design (Phase 2, not yet started)

Evaluation corpus (subset for scoring, NOT full generation set):

Yoruba:  1,000 proverbs (sampled from 2,000 generated)

English: 1,000 proverbs (sampled from 2,278 generated)

Arabic:    803 proverbs (all available   full set)

These three languages span low / mid / high resource tiers and form

the core comparison. French, German, Spanish serve as supplementary

high-resource controls.

NOTE: The Yoruba evaluation uses a 1,000-proverb subset, NOT the full

2,000 generated items. This is intentional   the remaining 1,000 serve

as a held-out development set for prompt tuning and ablations, ensuring

no data leakage between development and evaluation splits.

Zero-shot letter-choice protocol (A/B/C/D)

3 conditions: no_context (Task A), no_context (Task B), with_context (Task B)

Standard mode vs Reasoning mode (system prompt difference)

15-run evaluation matrix across model sizes

Models to evaluate:

Base: LLaMA-3.1-8B, LLaMA-3.3-70B, Gemma-4 (new), Qwen3-235B

AfriqueLLM: AfriqueLlama-8B, AfriqueGemma-12B, AfriqueQwen-14B

Proprietary (if budget allows): GPT-4o, Claude

9.3 Additional Evaluation Methods (teammate contributions)

Fill-in-the-Blank / Cloze Task (Iremide)

ProverbEval (Azime et al.) did NOT include fill-in-the-blank   this

is a novel contribution unique to ProverbGap.

Design:

1. Take the correct meaning (literal for Task A, cultural for Task B).

2. Mask one semantically critical word or phrase (the "cloze target").

Example: "A person who ___ others will eventually face consequences."

3. The model receives the proverb + the masked sentence and must

predict the missing span.

4. Scoring uses token-overlap and embedding-based metrics:

BERTScore (semantic similarity of predicted vs gold span)

BLEU (n-gram precision)

ChrF++ (character-level F-score   important for morphologically

rich languages like Yoruba and Arabic)

5. Evaluation will use the same 1,000 Yoruba / 1,000 English / 803

Arabic subset to stay consistent with the MCQ evaluation.

Why this matters: Cloze tasks test productive knowledge (generating

the right word), whereas MCQs test receptive knowledge (selecting the

right option). A model that scores 85% on MCQ but 40% on cloze for

Yoruba proverbs reveals a deeper gap   it can recognise cultural

meaning but cannot produce it.

Text Generation / Free-form Explanation (Jesuyanmife)

Design:

1. Given a proverb, the model must generate a free-text explanation

of its meaning (literal and cultural) without any answer options.

2. Four prompting strategies are tested:

(a) Zero-shot:     "Explain the meaning of this proverb."

(b) Zero-shot+CoT: "Think step by step, then explain."

(c) Few-shot:      3 proverb–explanation exemplars provided.

(d) Few-shot+CoT:  3 exemplars with explicit reasoning chains.

3. Two reasoning-language formats:

English reasoning:       CoT chain is in English.

Cross-lingual reasoning: CoT chain is in the proverb's

source language (e.g., Yoruba reasoning for Yoruba proverbs).

4. Scoring metrics:

BERTScore  (semantic overlap with gold explanation)

BLEU       (n-gram precision)

ChrF++     (character-level F-score)

COMET      (neural translation-quality metric, trained on DA)

COMETKiwi  (reference-free quality estimation variant)

5. Core hypothesis: Cross-lingual CoT (reasoning in Yoruba) may

improve tone-mark accuracy and idiomatic phrasing for Yoruba

proverbs compared to English-only CoT, because the model stays

in the source-language embedding space.

Why both tracks matter: MCQ (receptive) + Cloze (productive) +

Generation (open-ended) form a three-level evaluation pyramid.

Together they give a much richer picture of cultural reasoning

than any single format alone   which is exactly the "unified work"

Steven suggested submitting.

9.4 Artifacts to Release

ProverbGap MCQ Dataset (HuggingFace)   ~32,000 items, CC BY 4.0 / CC BY-NC 4.0

ProverbGap Evaluation Code (GitHub)   MIT license

Generation pipeline code   reproducible notebook with all API calls logged

Shortcut audit toolkit   reusable blind evaluator protocol

10. TIMELINE AND DEADLINES

Target Venue A   EMNLP 2026 (Budapest, Hungary, October 24-29, 2026)

Route: Submit to ACL Rolling Review (ARR) May 2026 cycle → commit to EMNLP.

Key dates:

ARR May 2026 submission opens:          May 25, 2026

Reviewer registration (ALL authors):    May 27, 2026

Author response & discussion:           July 7 – July 13, 2026

Meta-review released:                   July 30, 2026

EMNLP commitment deadline:              August 2, 2026

Notification of acceptance:             August 20, 2026

Camera-ready due:                       September 20, 2026

Conference:                             October 24 – 29, 2026

Relevant tracks: "Multilingualism and Cross-Lingual NLP",

"Resources and Evaluation"

Theme: "New Missions for NLP Research"

Note: ARR May 2026 policy requires authors to declare EMNLP 2026 as

preferred venue at submission time; this choice is BINDING for EMNLP.

Target Venue B   NeurIPS 2026 Evaluations & Datasets Track

(Sydney, Australia; satellites in Atlanta & Paris; Dec 6-12, 2026)

Key dates:

Abstract submission deadline:           May 4, 2026  (AoE)

Full paper submission deadline:         May 6, 2026  (AoE)

Author notification:                    September 24, 2026

Conference:                             December 6 – 12, 2026

Note: The track was renamed from "Datasets & Benchmarks" to

"Evaluations & Datasets" for 2026, with expanded scope for evaluation

methodology papers   our benchmark + audit protocol fits well.

Steven's suggestion (April 24): Submit to either NeurIPS or EMNLP as a

single unified work combining MCQ + Fill-in-Blank + Generation evaluation.

Venue decision strategy: The progress we make in the next 7–10 days

will determine the target. If we can complete MCQ regeneration, run the

evaluation on the 1,000-proverb Yoruba subset, and produce core result

tables by May 3, we will submit to NeurIPS 2026 (abstract May 4, paper

May 6). If that timeline proves too aggressive, we default to EMNLP 2026

(ARR May 25) which gives us three additional weeks   ample time for a

more polished submission with all three evaluation formats integrated.

Our remaining work:

Week 1 (Apr 25 – May 1):  Complete MCQ regeneration (resume Kaggle runs

until all 36 CSVs refreshed). Run length

patch on flagged items. Finalize audit.

Week 2 (May 2 – 8):       Run Phase 2 evaluation on 1,000 Yoruba /

1,000 English / 803 Arabic (15 conditions).

AfriqueLLM evaluation on Yoruba subset.

[If targeting NeurIPS: submit abstract May 4,

full paper May 6.]

Week 3 (May 9 – 15):      Integrate Iremide's fill-in-blank results and

Jesuyanmife's generation results. Begin paper

writing (intro, related work, method).

Week 4 (May 16 – 22):     Complete paper draft. Internal review with

Week 5 (May 23 – 29):     [If targeting EMNLP: submit to ARR May 25.]

ALL authors register as reviewers by May 27.

11. LITERATURE GROUNDING (KEY CITATIONS)

| Paper | Venue | Year | Relevance |
| --- | --- | --- | --- |
| Azime et al. (ProverbEval) | NAACL Find. | 2025 | Prior work, 4 Ethiopian langs, ~500 proverbs |
| Alhazmi et al. | EMNLP | 2024 | Distractor generation survey |
| DiVERT (Fernandez et al.) | EMNLP | 2024 | Math MCQ distractor generation |
| INCLUDE (Romanou et al.) | ICLR | 2025 | Multilingual regional knowledge benchmark |
| Global MMLU (Singh et al.) | ACL | 2025 | Multilingual evaluation at scale |
| AfroBench (Ojo et al.) | ACL Find. | 2025 | African language LLM evaluation |
| IrokoBench (Adelani et al.) | NAACL | 2025 | 17 African language benchmark |
| BenchMarker (Balepur et al.) | arXiv | 2026 | Shortcut detection in MCQ benchmarks |
| AfriqueLLM (Yu et al.) | arXiv | 2026 | Africa-adapted LLMs for eval |
| Zheng et al. | ICLR | 2024 | Position bias in MCQ evaluation |
| Pezeshkpour & Hruschka | NAACL Find. | 2024 | LLM sensitivity to answer order |

11.1 VERIFIED REFERENCE URLS

[1]  Azime et al. (ProverbEval)   NAACL 2025 Findings

https://aclanthology.org/2025.findings-naacl.350/

[2]  Alhazmi et al.   EMNLP 2024

https://aclanthology.org/2024.emnlp-main.799/

[3]  DiVERT (Fernandez et al.)   EMNLP 2024

https://aclanthology.org/2024.emnlp-main.512/

[4]  INCLUDE (Romanou et al.)   ICLR 2025

https://arxiv.org/abs/2411.19799

[5]  Global MMLU (Singh et al.)   ACL 2025

https://aclanthology.org/2025.acl-long.919/

[6]  AfroBench (Ojo et al.)   ACL 2025 Findings

https://aclanthology.org/2025.findings-acl.976/

[7]  IrokoBench (Adelani et al.)   NAACL 2025

https://aclanthology.org/2025.naacl-long.139/

[8]  BenchMarker (Balepur et al.)   arXiv, February 2026

https://arxiv.org/abs/2602.06221

[9]  AfriqueLLM (Yu et al.)   arXiv, January 2026

https://arxiv.org/abs/2601.06395

[10] Zheng et al.   ICLR 2024 (Spotlight)

https://arxiv.org/abs/2309.03882

[11] Pezeshkpour & Hruschka   NAACL 2024 Findings

https://aclanthology.org/2024.findings-naacl.130/

11.2 ETHICAL CONSIDERATIONS

Data sourcing: All proverb corpora are sourced from publicly available

datasets (HuggingFace, web-scraped) or published books with attribution.

Yoruba proverbs are derived from a copyrighted collection; only our MCQ

items (not raw proverbs) are released, under CC BY-NC 4.0.

Cultural sensitivity: Proverbs encode culturally specific values and

worldviews. We do not editorialize or judge the cultural content. The

benchmark evaluates LLM understanding, not cultural correctness.

Bias: LLM-generated distractors may inherit biases from training data.

Our shortcut audit mitigates surface-level biases; deeper cultural

biases are acknowledged as a limitation.

Dual use: ProverbGap is designed for LLM evaluation and research.

We do not foresee harmful dual-use scenarios, but we release data with

documentation (datasheets) and access-request mechanisms for Yoruba data.

11.3 SCOPE AND LIMITATIONS

Languages: 6 languages sampled from 3 resource tiers. This does not

represent the full diversity of world languages or African languages.

Proverb selection: Proverbs are drawn from available digital corpora,

which may not represent the full oral tradition of each language.

Small corpora: French (160), German (141), Spanish (62) provide

directional evidence but lack statistical power for fine-grained

analysis. Results for these languages are reported with confidence

intervals.

Automation: LLM-generated distractors are validated by audit but not

by human cultural experts. Future work should include human validation.

Single evaluator culture: The shortcut audit uses a single LLM as

blind evaluator; multi-model committees would be more robust.

12. ADDRESSING POTENTIAL REVIEWER CONCERNS

Q: "Why not use human annotators for distractors?"

A: ProverbEval used humans and scaled to only 500 items. We demonstrate

LLM-generated distractors can achieve equivalent quality at 10x scale,

validated by the blind shortcut audit. DiVERT (EMNLP 2024) established

that LLM-generated math MCQ distractors can match or exceed human-written

quality. Alhazmi et al. (EMNLP 2024) survey broader evidence for LLM

distractor quality across multiple domains.

Q: "French/German/Spanish are high-resource, not mid-resource."

A: We frame them as a high-resource control group, not mid-resource.

Arabic is our mid-resource representative. The core finding compares

Yoruba (low) vs Arabic (mid) vs English (high).

Q: "Why not include newer models like GPT-4o or Gemma 4?"

A: Budget constraint   we use free-tier APIs exclusively. However, our

evaluation phase will test on Gemma 4 (newly released April 2026)

and AfriqueLLM models. The benchmark is model-agnostic; anyone can

evaluate any model on our released dataset.

Q: "The corpus sizes are unbalanced (2,278 English vs 62 Spanish)."

A: We report per-language metrics with confidence intervals. The primary

comparison is between resource tiers (Yoruba 2,000 vs English 2,278),

not between small languages. French/German/Spanish provide directional

evidence for the high-resource control condition.

Q: "How do you know the Cultural Reasoning Gap isn't just harder questions?"

A: The two-task design controls for this. Task A and Task B use the SAME

proverbs with the SAME model   only the correct answer differs (literal

vs cultural meaning). Any accuracy difference is attributable to the

type of knowledge required, not question difficulty.

Q: "Why automate distractor generation instead of curating by hand?"

A: Scale and reproducibility. Our automated pipeline processes 5,444

proverbs × 3 strategies in hours, while human annotation took weeks

for 500 items in ProverbEval. The shortcut audit validates quality.

Q: "Is the Yoruba data ethically sourced?"

A: The source book is acknowledged. We release only the generated MCQ

items (our contribution) under CC BY-NC 4.0, not the raw proverbs.

A Yoruba language datasheet will accompany the submission.

7. Current status: MCQ regeneration is live on Kaggle (April 24).

Cerebras ZS running, NVIDIA fallback active. Estimated 2-3 more

sessions to complete. Length patch and Phase 2 evaluation follow.

14. TEAM STATUS AND REALISTIC PACE (TRANSPARENCY NOTE)

April 2026 has been an unusually disruptive month for the team. Multiple

members have had major life transitions happening in parallel:

New jobs:    Team members starting new positions with onboarding

New internships: Summer internship commitments beginning

School:   End-of-semester coursework, exams, and deadlines

These are the honest reasons why progress has been slower than our

original timeline projected. We are NOT blocked on technical capability

the pipeline works, the data is clean, the code is debugged. We are

blocked on available person-hours.

Plan for this weekend (April 26–27, 2026):

Parallel processing push: All available team members will run

concurrent Kaggle sessions using the checkpoint-resume pipeline

and parallel API key rotation to maximise throughput.

Goal: Complete as much of the 36-CSV regeneration as possible in

two back-to-back 12-hour Kaggle sessions.

Key iteration: Each session will cycle through all 8 Groq keys +

Cerebras + NVIDIA fallback in parallel, targeting ~4,000-6,000

rows per session.

Progress from this weekend will directly determine our venue:

If we finish regeneration + start evaluation → NeurIPS (May 4-6).

If we need more time → EMNLP (May 25) with a stronger submission.

Bottom line for Steven: The team is committed, the work is real, and

the pipeline is production-ready. The slowdown is a scheduling problem,

not a technical one. We will push hard this weekend and have a clear

venue decision by Monday April 28.